## AssetList
Asset | Priority
Pre-Trained AI Model Library | Critical
Cloud Storage | Critical
Data Integration Platform | High
Customer Relationship Management (CRM) Appication | Medium
Data Annotation Application | Low

## RiskRegister
ID | Description | Application | Likelihood | Impact | Priority | Risk Owner | Mitigation Strategy | Residual Risk | Current Controls | Status | Category
1 | Data Breach | Data Integration Platform | Medium | Medium | Medium | Development | Encryption, logging, and network monitoring | Low | 24/7 Cybersecurity Monitoring Team. Client data is separated from VISION's own infrastructure. (Assumed: Encryption) | Mitigated | Compliance
|  | Cloud Storage | High | Critical | Critical | Security | Encryption, logging, and network monitoring | High | 24/7 Cybersecurity Monitoring Team. Client data is separated from VISION's own infrastructure. (Assumed: Encryption) | Mitigated | Compliance
|  | Data Annotation Application | Low | Medium | Low | DS/ML | Encryption, logging, and network monitoring | Low | 24/7 Cybersecurity Monitoring Team. Client data is separated from VISION's own infrastructure. (Assumed: Encryption) | Mitigated | Compliance
|  | Customer Relationship Management (CRM) System | Low | Medium | Low | Security | Encryption, logging, and network monitoring | Low | 24/7 Cybersecurity Monitoring Team. Client data is separated from VISION's own infrastructure. (Assumed: Encryption) | Mitigated | Compliance
|  | Pre-Trained AI Model Library | Medium | Critical | High | DS/ML | Encryption, logging, and network monitoring | Medium | 24/7 Cybersecurity Monitoring Team. Client data is separated from VISION's own infrastructure. (Assumed: Encryption) | Mitigated | Compliance
2 | Unauthorized Access | Data Integration Platform | High | High | High | Development | Access Control Lists | Medium | Assumed: Access Control Lists | In Progress | General
|  | Cloud Storage | Medium | Critical | High | Security | Access Control Lists | Medium | Assumed: Access Control Lists | In Progress | General
|  | Customer Relationship Management (CRM) System | Medium | Medium | Medium | Client Relationships | Access Control Lists | Low | Assumed: Access Control Lists | In Progress | General
3 | Code Injections/Data Poisoning | Data Integration Platform | Medium | High | Medium | Development | Regular Tests and input verification/normalization | Low | None | Identified | General
|  | Data Annotation Application | Medium | High | High | DS/ML | Regular Tests and input verification/normalization | Medium | None | Identified | General
|  | Pre-Trained AI Model Library | Medium | High | High | DS/ML | Regular Tests and input verification/normalization | Medium | None | Identified | General
4 | Adversarial Attacks | Data Integration Platform | High | Critical | Critical | Development | Adversarial training and input validation | High | Assumed: Input Validation | In Progress | General
|  | Data Annotation Application | High | Critical | Critical | DS/ML | Adversarial training and input validation | High | Assumed: Input Validation | In Progress | General
|  | Pre-Trained AI Model Library | Medium | Critical | High | DS/ML | Adversarial training and input validation | Medium | Assumed: Input Validation | In Progress | General
5 | Model Poisoning | Data Integration Platform | High | Critical | Critical | Development | Anomoly detection and robustness testing | High | None | Identified | General
|  | Data Annotation Application | High | Critical | Critical | DS/ML | Anomoly detection and robustness testing | High | None | Identified | General
|  | Pre-Trained AI Model Library | Medium | Critical | High | DS/ML | Anomoly detection and robustness testing | Medium | None | Identified | General
6 | MitM | Data Integration Platform | High | High | High | Security | Encryption ans VPN Connections | Medium | None | Identified | General
|  | Cloud Storage | Medium | High | High | Security | Encryption ans VPN Connections | Medium | None | Identified | General
|  | Customer Relationship Management (CRM) System | Medium | Medium | Medium | Client Relationships | Encryption ans VPN Connections | Low | None | Identified | General
7 | Phishing | Data Integration Platform | Medium | High | High | Security | MFA | Medium | Assumed: MFA and employee training (both for VISION and the client) | In Progress | General
|  | Customer Relationship Management (CRM) System | Low | Medium | Medium | Security | MFA | Low | Assumed: MFA and employee training (both for VISION and the client) | In Progress | General
8 | Third-Party Risks | Cloud Storage | Medium | High | High | Security | Establish Procurement and Testing Protocols | Medium | Assumed: Vendor and contractor management processes | In Progress | General
|  | Data Annotation Application | Medium | Medium | Medium | DS/ML | Establish Procurement and Testing Protocols | Low | Assumed: Vendor and contractor management processes | In Progress | General
|  | Customer Relationship Management (CRM) System | Medium | Medium | Medium | Client Relationships | Establish Procurement and Testing Protocols | Low | Assumed: Vendor and contractor management processes | In Progress | General
9 | Non-Compliance with Data Protection Policies | Data Integration Platform | Medium | High | High | GRC | Strong validation, verification, and encryption. GRC and Legal processes | Medium | All data used by VISION is stored in the United States. Currently, all of their clients are US companies (only HIPPA regulations are followed). | Mitigated | Compliance
|  | Cloud Storage | High | Critical | Critical | GRC | Strong validation, verification, and encryption. GRC and Legal processes | High | All data used by VISION is stored in the United States. Currently, all of their clients are US companies (only HIPPA regulations are followed). | Mitigated | Compliance
|  | Data Annotation Application | Medium | High | High | GRC | Strong validation, verification, and encryption. GRC and Legal processes | Medium | All data used by VISION is stored in the United States. Currently, all of their clients are US companies (only HIPPA regulations are followed). | Mitigated | Compliance
|  | Customer Relationship Management (CRM) System | Low | Medium | Medium | GRC | Strong validation, verification, and encryption. GRC and Legal processes | Low | All data used by VISION is stored in the United States. Currently, all of their clients are US companies (only HIPPA regulations are followed). | Mitigated | Compliance
|  | Pre-Trained AI Model Library | Medium | Critical | High | GRC | Strong validation, verification, and encryption. GRC and Legal processes | Medium | All data used by VISION is stored in the United States. Currently, all of their clients are US companies (only HIPPA regulations are followed). | Mitigated | Compliance
10 | Privilege Escalation | Data Integration Platform | High | Critical | Critical | DS/ML | Detailed and Comprehensive Onboarding and Offboarding procedure. | High | None | Identified | General
|  | Cloud Storage | Medium | Critical | High | Security | Detailed and Comprehensive Onboarding and Offboarding procedure. | Medium | None | Identified | General
|  | Data Annotation Application | Medium | High | High | DS/ML | Detailed and Comprehensive Onboarding and Offboarding procedure. | Medium | None | Identified | General
|  | Customer Relationship Management (CRM) System | Low | High | Medium | Client Relationships | Detailed and Comprehensive Onboarding and Offboarding procedure. | Low | None | Identified | General
11 | Outdated Software | Data Integration Platform | Medium | Medium | Medium | Change Control Board (CCB) | Perform Regular Software Updates | Low | None | Identified | General
|  | Cloud Storage | Medium | High | High | Change Control Board (CCB) | Perform Regular Software Updates | Medium | None | Identified | General
|  | Data Annotation Application | High | High | High | Change Control Board (CCB) | Perform Regular Software Updates | Medium | None | Identified | General
|  | Customer Relationship Management (CRM) System | High | Medium | Medium | Change Control Board (CCB) | Perform Regular Software Updates | Low | None | Identified | General
|  | Pre-Trained AI Model Library | Medium | Critical | High | Change Control Board (CCB) | Perform Regular Software Updates | Medium | None | Identified | General
12 | Unpatched Vulnerabilities | Data Integration Platform | Medium | High | High | Change Control Board (CCB) | Patch all known vulnerabilities. Replace legacy technology. Implement Change Management Processes | Medium | None | Identified | General
|  | Cloud Storage | Medium | Critical | Critical | Change Control Board (CCB) | Patch all known vulnerabilities. Replace legacy technology. Implement Change Management Processes | High | None | Identified | General
|  | Data Annotation Application | Medium | High | High | Change Control Board (CCB) | Patch all known vulnerabilities. Replace legacy technology. Implement Change Management Processes | Medium | None | Identified | General
|  | Customer Relationship Management (CRM) System | Medium | Medium | Medium | Change Control Board (CCB) | Patch all known vulnerabilities. Replace legacy technology. Implement Change Management Processes | Low | None | Identified | General
|  | Pre-Trained AI Model Library | High | Critical | Critical | Change Control Board (CCB) | Patch all known vulnerabilities. Replace legacy technology. Implement Change Management Processes | High | None | Identified | General
13 | Insecure Configurations | Data Integration Platform | Medium | High | High | Security | Perform pen testing and threat hunting exercises | Medium | None | Identified | General
|  | Cloud Storage | High | Critical | Critical | Security | Perform pen testing and threat hunting exercises | High | None | Identified | General
|  | Data Annotation Application | Medium | High | High | Security | Perform pen testing and threat hunting exercises | Medium | None | Identified | General
|  | Customer Relationship Management (CRM) System | Medium | Medium | Medium | Security | Perform pen testing and threat hunting exercises | Low | None | Identified | General
|  | Pre-Trained AI Model Library | Medium | Critical | High | Security | Perform pen testing and threat hunting exercises | Medium | None | Identified | General

## Data
Asset Risk Pre-Mitigation
# of Critical Risks | 10
# of High Risks | 24
# of Medium Risks | 13
# of Low Risks | 2
Asset Risk Post-Mitigation
# of Critical Risks | 0
# of High Risks | 10
# of Medium Risks | 24
# of Low Risks | 15

## RiskMatrix
Impact
|  | Critical | High | Medium | Low
Likelihood | Critical | Critical | Critical | High | High
| High | Critical | High | High | Medium
| Medium | High | High | Medium | Low
| Low | High | Medium | Low | Low